## Slide 1: PROJECT MANAGEMENT AND PLANNING RESITATION

## Slide 2
Compress the given network fully. The direct cost is 10.000 TL.
TN = 36 days
C N = 10 000 TL
Critical path: B-C-D
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
Example 1.

## Slide 3
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
10 0/200
New project duration = 26 days
New project cost = 10 000 + 10*200 = 12 000 TL
Critical path: B-C-D
* There is no network limitation since the compression of 10 days is smaller than the float of 14 days in the B-C-D path.
I. Crashing
Ex 1.

## Slide 4
0
1
2
3
4
0 0
B
E
D
C
A
6 2/300
6
10 1/400
12 9/100
10 0/200
T2 = 22 days
C2 = 12 000 + 4*300= 13 200 TL
Critical path: B-C-D and A-E
* There is a network limitation because if we compress B by 6 days, the parallel path which has a float of 4 days becomes automatically critical. That means, it would be waste of money if we compress B by more than 4 days.
II. Crashing
Ex 1.

## Slide 5
T3 = 20 days
C3= 13 200 + 100*2 + 300*2= 14 000 TL
For further compression, it must involve equal decreases in both critical paths, because otherwise the project duration will not be reduced. 1 st chain: B-C-D, 2 nd chain: A-E
There is a network limitation because if we compress A by 9 days, the 7 days will have no effect on the Final duration. B can only be compressed by 2 days
III. Crashing
0
1
2
3
4
0 0
B
E
D
C
A
4 0/300
6
10 1/400
10 7/100
10 0/200
1 st chain: B-C-D  B (300)
2 nd chain: A-E  A (100)
Ex 1.

## Slide 6
T4 = 20 days
C4= 14 000 + 7*100 + 400= 15 100 TL
That is why this compression is cometimes called as ‘’useless crash’’.
Once the activity on a critical chain have been fully crashed, then there is no possibility to compress the network further. There is no need to crash other activities since this will add to the cost but will have no effect on the project duration
To achieve ‘all crash’ situation:
IV. Crashing
0
1
2
3
4
0 0
B
E
D
C
A
4 0/300
6
9 0/400
3 0/100
10 0/200
1 st chain: B-C-D  B (300)
2 nd chain: A-E  A (100)
Ex 1.

## Slide 7
If the indirect cost is 230 ₺ / day, what is the optimum duration and associated cost? Draw the direct and indirect cost curves.
duration | direct | indirect |  | total
36 | 10000 | 230x36= | 8280 | 18280
35 | 10200 | 230x35= | 8050 | 18250
34 | 10400 | 230x34= | 7820 | 18220
33 | 10600 | 230x33= | 7590 | 18190
32 | 10800 | 230x32= | 7360 | 18160
31 | 11000 | 230x31= | 7130 | 18130
30 | 11200 | 230x30= | 6900 | 18100
29 | 11400 | 230x29= | 6670 | 18070
28 | 11600 | 230x28= | 6440 | 18040
27 | 11800 | 230x27= | 6210 | 18010
26 | 12000 | 230x26= | 5980 | 17980
25 | 12300 | 230x25= | 5750 | 18050
24 | 12600 | 230x24= | 5520 | 18120
23 | 12900 | 230x23= | 5290 | 18190
22 | 13200 | 230x22= | 5060 | 18260
21 | 13600 | 230x21= | 4830 | 18430
20 | 14000 | 230x20= | 4600 | 18600
20 | 15100 | 230x20= | 4600 | 19700
Chart: Days
| 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 20
 | 18280 | 18250 | 18220 | 18190 | 18160 | 18130 | 18100 | 18070 | 18040 | 18010 | 17980 | 18050 | 18120 | 18190 | 18260 | 18430 | 18600 | 19700
Chart: Days
| 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 20
 | 8280 | 8050 | 7820 | 7590 | 7360 | 7130 | 6900 | 6670 | 6440 | 6210 | 5980 | 5750 | 5520 | 5290 | 5060 | 4830 | 4600 | 4600
Chart: Days
| 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 20
 | 10000 | 10200 | 10400 | 10600 | 10800 | 11000 | 11200 | 11400 | 11600 | 11800 | 12000 | 12300 | 12600 | 12900 | 13200 | 13600 | 14000 | 15100
Topt = 26
Copt = 17980 ₺

## Slide 8
Example 2.
Find the least cost schedule for the network shown below.
Act | Duration |  | Cost | 
 | Normal | Crashed | Normal | Crashed
A | 4 | 2 | 400 ₺ | 500 ₺
B | 8 | 5 | 800 ₺ | 980 ₺
C | 3 | 2 | 600 ₺ | 700 ₺
D | 10 | 6 | 500 ₺ | 600 ₺
E | 8 | 6 | 800 ₺ | 950 ₺
F | 7 | 4 | 700 ₺ | 1.000 ₺
Overhead cost = 100 ₺ / day
(indirect cost)
0
B
E
D
C
A
3
7
10
8
4
8
F
1
2
3
4

## Slide 9
Ex 2.
Act | Duration |  | Cost |  | 
 | Normal | Crashed | Normal | Crashed | slope
A | 4 | 2 | 400 ₺ | 500 ₺ | (500-400) / (4-2) = 50 ₺ / day
B | 8 | 5 | 800 ₺ | 980 ₺ | 60 ₺
C | 3 | 2 | 600 ₺ | 700 ₺ | 100 ₺
D | 10 | 6 | 500 ₺ | 600 ₺ | 25 ₺
E | 8 | 6 | 800 ₺ | 950 ₺ | 75 ₺
F | 7 | 4 | 700 ₺ | 1.000 ₺ | 100 ₺
Direct costs = 400 + 800 + 600 + 500 + 800+ 700 = 3800 ₺
Indirect costs = 16 x 100 = 1600 ₺
Total = 5400 ₺
0
0 0
B
E
D
C
A
3
1/100
7
3/100
10
4/25
8
2/75
4
2/50
8
3/60
F
16 16
4 6
8 8
8 9
1
2
3
4

## Slide 10
Ex 2.
T1 = 15 days
D.C = 3800 + 60 = 3860 ₺
I.C = 15 x 100 = 1500 ₺
Total = 5360 ₺
I. Crash
0
0 0
B
E
D
C
A
3
1/100
7
3/100
10
4/25
8
2/75
4
2/50
7
2/60
F
15 15
4 5
7 7
7 8
1
2
3
4
Critical path = B60-E75
Crash B by 1

## Slide 11
Ex 2.
T2 = 14 days
D.C = 3860 + 60 = 3920 ₺
I.C = 14 x 100 = 1400 ₺
Total = 5320 ₺
II. Crash
0
0 0
B
E
D
C
A
3
1/100
7
3/100
10
4/25
8
2/75
4
2/50
6
1/60
F
14 14
4 4
6 6
6 7
1
2
3
4
Critical path = B60-E75
Crash B by 1

## Slide 12
Ex 2.
T3 = 13 days
D.C = 3920 + 60 + 25 = 4005 ₺
I.C = 13 x 100 = 1300 ₺
Total = 5305 ₺
III. Crash
0
0 0
B
E
D
C
A
3
1/100
7
3/100
9
3/25
8
2/75
4
2/50
5
0/60
F
13 13
4 4
5 5
5 6
1
2
3
4
Critical path = B60-E75 and A50-D25
Crash B and D by1

## Slide 13
Ex 2.
T4 = 12 days
D.C = 4005 + 75 + 25 = 4105 ₺
I.C = 12 x 100 = 1200 ₺
Total = 5305 ₺ (same with the third crash)
IV. Crash
0
0 0
B
E
D
C
A
3
1/100
7
3/100
8
2/25
7
1/75
4
2/50
5
0/60
F
12 12
4 4
5 5
5 5
1
2
3
4
Critical path = B60-E75 and A50-D25
Crash E and D by1

## Slide 14
Ex 2.
T5 = 11 days
D.C = 4105 + 75 + 25 + 100 = 4305 ₺
I.C = 11 x 100 = 1100 ₺
Total = 5405 ₺ (missed the optimum point)
*If one of the critical path is completely crashed (B-E), stop then.
V. Crash
0
0 0
B
E
D
C
A
3
1/100
6
2/100
7
1/25
6
0/75
4
2/50
5
0/60
F
11 11
4 4
5 5
5 5
1
2
3
4
Critical path = B60-E75 / A50-D25 / B60-F100
Crash E, D and F by 1

## Slide 15
Least cost = 5305 ₺
Optimum time 12 or 13 days
Chart: Days
| 16 | 15 | 14 | 13 | 12 | 11
 | 5400 | 5360 | 5320 | 5305 | 5305 | 5405

## Slide 16
Example 3.
Normal duration = 19 days
Normal cost = 25300 ₺
Indirect cost = 19 x 120 = 2280 ₺
Total cost = 27 580 ₺
1
B
E
D
C
A
6 (50,60,60)
F
4
3
2
7
6
5
14 14
6 6
5 6
4 6
0 0
G
I
H
14 15
19 19
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
4 (30,60,80)
4 (40,50)
10 (20,20,20)
5 (10,10,30,50)
d3
d2
d1

## Slide 17
Ex 3.
Normal duration = 18 days
Normal cost = 25300 + 10 = 25310 ₺
Indirect cost = 18 x 120 = 2160 ₺
Total cost = 27 470 ₺
1
B
E
D
C
A
6 (50,60,60)
F
4
3
2
7
6
5
14 14
6 6
5 6
4 6
0 0
G
I
H
14 14
18 18
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
4 (30,60,80)
4 (40,50)
10 (20,20,20)
4 (10,10,30,50)
d3
d2
d1
Critical path = A50-F80-H10
Crash H by 1
I. Crash

## Slide 18
Ex 3.
T = 17 days
D.C= 25310 + 40 = 25350 ₺
I.C. = 17 x 120 = 2040 ₺
T.C = 27 390 ₺
1
B
E
D
C
A
6 (50,60,60)
F
4
3
2
7
6
5
14 14
6 6
5 6
4 6
0 0
G
I
H
14 14
17 17
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
3 (30,60,80)
4 (40,50)
10 (20,20,20)
3 (10,10,30,50)
d3
d2
d1
Critical path = A50-F80-H10 / A50-F80-I30
1) A  50,
2) F  80,
3) H + I  30+10=40
Decision H and I
II. Crash

## Slide 19
Ex 3.
T = 16 days
D.C= 25350 + 50 = 25400 ₺
I.C. = 16 x 120 = 1920 ₺
T.C = 27 320 ₺
1
B
E
D
C
A
5 (50,60,60)
F
4
3
2
7
6
5
13 13
5 5
5 5
4 5
0 0
G
I
H
13 13
16 16
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
3 (30,60,80)
4 (40,50)
10 (20,20,20)
3 (10,10,30,50)
d3
d2
d1
Critical path = A50-F80-H30 / A50-F80-I60
1) A  50,
2) F  80,
3) H + I  30+60=90
Decision A
III. Crash

## Slide 20
Ex 3.
T = 15 days
D.C= 25400 + 80 = 25480 ₺
I.C. = 15 x 120 = 1800 ₺
T.C = 27 280 ₺
1
B
E
D
C
A
5 (50,60,60)
F
4
3
2
7
6
5
12 12
5 5
5 5
4 5
0 0
G
I
H
12 12
15 15
9 (30,30,30)
7 (80,110)
5 (40,50)
6 (30,30,40)
3 (30,60,80)
4 (40,50)
10 (20,20,20)
3 (10,10,30,50)
d3
d2
d1
Critical path = A60-F80-H30 / A60-F80-I60 / B40-F80-H30 / B40-F80-I60
1) A + B  60+40=100,
2) F  80,
3) H + I  30+60=90
Decision F
IV. Crash

## Slide 21
Ex 3.
T = 14 days
D.C= 25480 + 90 = 25570 ₺
I.C. = 14 x 120 = 1680 ₺
T.C = 27 250 ₺
1
B
E
D
C
A
5 (50,60,60)
F
4
3
2
7
6
5
12 12
5 5
5 5
4 4
0 0
G
I
H
12 12
14 14
9 (30,30,30)
7 (80,110)
5 (40,50)
6 (30,30,40)
2 (30,60,80)
4 (40,50)
10 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
Critical path = A60-F110-H30 / A60-F110-I60 / B40-F110-H30 / B40-F110-I60
1) A + B  60+40=100,
2) F  110,
3) H + I  30+60=90
Decision H+I
V. Crash

## Slide 22
Ex 3.
T = 13 days
D.C= 25570 + 120 = 25690 ₺
I.C. = 13 x 120 = 1560 ₺
T.C = 27 250 ₺
1
B
E
D
C
A
4 (50,60,60)
F
4
3
2
4
6
5
11 11
4 4
4 4
4 4
0 0
G
I
H
11 11
13 13
9 (30,30,30)
7 (80,110)
4 (40,50)
6 (30,30,40)
2 (30,60,80)
4 (40,50)
9 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
C. P. = A60-F110-H50 / A60-F110-I80 / A60-E30 / B40-F110-H50 / B40-F110-I80 / B40-E30 / C40-G20
1) A + B  60+40=100,
2) E + F  30+110=140,
3) H + I + E  50+80+30=160
Decision A + B + G
VI. Crash
Independent crash G by 1

## Slide 23
Ex 3.
T = 12 days
D.C= 25690 + 150 = 25840 ₺
I.C. = 12 x 120 = 1440 ₺
T.C = 27 280 ₺
1
B
E
D
C
A
3 (50,60,60)
F
4
3
2
7
6
5
10 10
3 3
3 3
3 3
0 0
G
I
H
10 10
12 12
9 (30,30,30)
7 (80,110)
3 (40,50)
6 (30,30,40)
2 (30,60,80)
3 (40,50)
9 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
C.P.
A60-F110-H50
A60-F110-I80
A60-E30
B50-F110-H50
B50-F110-I80
B50-E30 C40-G20
C40-F110-H50
C40-F110-I80
C40-E30
VII. Crash
1) A + B + C  60+50+40=150,
2) E + F + G 30+110+20=160,
3) H + I + E + G  50+80+30+20=180
Decision A + B + C

## Slide 24
Ex 3.
T = 11 days
D.C= 25840 + 160 = 26000 ₺
I.C. = 11 x 120 = 1320 ₺
T.C = 27320 ₺
1
B
E
D
C
A
3 (50,60,60)
F
4
3
2
7
6
5
9 9
3 3
3 3
3 3
0 0
G
I
H
9 9
11 11
8 (30,30,30)
6 (80,110)
3 (40,50)
6 (30,30,40)
2 (30,60,80)
3 (40,50)
8 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
A- F110-H50
A- F110-I80
A- E30
B- F110-H50
B- F110-I80
B- E30 C50-G20
C50-F110-H50
C50-F110-I80
C50-E30
VIII. Crash
1) E + F + G 30+110+20=160,
2) H + I + E + G  50+80+30+20=180
Decision E + F + G = 160

## Slide 25
Ex 3.
T = 10 days
D.C= 26000 + 180 = 26180 ₺
I.C. = 10 x 120 = 1200 ₺
T.C = 27380 ₺
1
B
E
D
C
A
3 (50,60,60)
F
4
3
2
7
6
5
9 9
3 3
3 3
3 3
0 0
G
I
H
9 9
10 10
7 (30,30,30)
6 (80,110)
3 (40,50)
6 (30,30,40)
1 (30,60,80)
3 (40,50)
7 (20,20,20)
1 (10,10,30,50)
d3
d2
d1
IX. Crash
1) E + H + I + G 30+ 50 + 80 +20=180,
2) E + H + I + C  30+ 50 + 80 +50=210
Decision  E + H + I + G = 180
A –F -H50
A –F -I80
A -E30
B –F -H50
B –F -I80
B -E30 C50-G20
C50-F -H50
C50-F -I80
C50-E30

## Slide 26
Ex 3.
Topt = 13 -14
T.C for optimum duration= 27250 ₺
As at least one of the critical paths is completely crashed, we should stop then.
A –F -H50
A –F -I80
A -E30
B –F -H50
B –F -I80
B -E30 C50-G20
C50-F -H50
C50-F -I80

## Slide 27
Example 4.
C0 = 1000 ₺
C3 = 1175 ₺
C6 = 1420 ₺
T0= 20 days
1
7
B (3/30)
5
A (2/X1)
2
4
3
6
5
13
D (3/40)
6
C (3/50)
2
G (1/30)
10
E (2/X2)
12
F (3/20)
10
H (3/10)

## Slide 28
Ex 4.
C.P. = B30-D40 / C50-F20-G30
Crash B+F = 50
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
5 6
6 6
6 6
0 0
17 17
19 19
13
D (3/40)
6
C (3/50)
2
G (1/30)
10
E (2/X2)
11
F (2/20)
10
H (3/10)
I. Crash
T1 = 19 days
C1 = 1000 + 50 = 1050 ₺

## Slide 29
Ex 4.
C.P. = B30-D40 / C50-F20-G30 / C50-D40
1) B+C  80
2) D+F  60
Decision  D+F
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
5 6
6 6
6 6
0 0
16 16
18 18
12
D (2/40)
6
C (3/50)
2
G (1/30)
10
E (2/X2)
10
F (1/20)
10
H (3/10)
II. Crash
T2 = 18 days
C2 = 1050 + 60 = 1110 ₺

## Slide 30
Ex 4.
C.P.
B30-D40
B30-EX2-G30
C50-F20-G30
C50-EX2-G30
C50-D40
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
5 6
6 6
6 6
0 0
15 15
17 17
11
D (1/40)
6
C (3/50)
2
G (1/30)
9
E (1/X2=5)
9
F (0/20)
10
H (3/10)
III. Crash
T3 = 17 days
C3 = 1110 + 65 = 1175 ₺
1) B+C  80
2) D+F+E  60+X2
C3 =1175
1175-1110=65 must be total crash cost
Decision  D+F+E and X2=5

## Slide 31
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
5 6
6 6
6 6
0 0
15 15
16 16
10
D (0/40)
6
C (3/50)
1
G (0/30)
9
E (1/5)
9
F (0/20)
10
H (3/10)
IV. Crash
T4 = 16 days
C4 = 1175 + 70 =1245 ₺
1) D+G  70
2) C+G  80
Decision  D+G

## Slide 32
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
C50-H10
1
5
B (1/30)
5
A (2/X1)
2
4
3
6
5
5 5
5 5
5 5
0 0
14 14
15 15
10
D (0/40)
5
C (2/50)
1
G (0/30)
9
E (1/5)
9
F (0/20)
10
H (3/10)
V. Crash
T5 = 15 days
C5 = 1245 + 80 =1325 ₺
Crash  B+C = 80

## Slide 33
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
C50-H10
1
4
B (0/30)
4
A (1/X1=15)
2
4
3
6
5
4 4
4 4
4 4
0 0
13 13
14 14
10
D (0/40)
4
C (1/50)
1
G (0/30)
9
E (1/5)
9
F (0/20)
10
H (3/10)
VI. Crash
T6 = 14 days
C6 = 1325+80+X1 = 1420 ₺
X1 = 15 ₺
Crash  A+B+C = 80 + X1
AX1-D40
AX1-E5-G30

## Slide 34
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
C50-H10
Topt = 15, 16
Copt = 2525 ₺
AX1-D40
AX1-E5-G30
As one of the critical path (B-D) is completely crashed, we should stop then.
If the indirect cost is 80 ₺ / day, what is the optimum duration and associated cost?
Duration | Direct cost | Indirect cost | Total cost
20 | 1.000 ₺ | 80x20=1600 | 2.600 ₺
19 | 1.050 ₺ | 80x19=1520 | 2.570 ₺
18 | 1.110 ₺ | 1440 | 2.550 ₺
17 | 1.175 ₺ | 1360 | 2.535 ₺
16 | 1.245 ₺ | 1280 | 2.525 ₺
15 | 1.325 ₺ | 1200 | 2.525 ₺
14 | 1.420 ₺ | 1120 | 2.540 ₺
Chart: Days
| 20 | 19 | 18 | 17 | 16 | 15 | 14
 | 2600 | 2570 | 2550 | 2535 | 2525 | 2525 | 2540

## Slide 35
Example 5.
A company is to complete work packages of “formworks, reinforcement, concrete, plastering and painting Works” for a 3 storey residential building. Firstly, the work package for the first floor will be executed after that for second floor and finally the construction will be completed by executing the work packages for the third floor.
3rd Floor
2nd Floor
1st Floor
Assumptions: There are 5 activities which are formworks, reinforcement, concrete, plastering and painting. There is only one team for each of the activities. Firstly formworks activity will be performed for the first floor, after that reinforcement, concrete, plastering and painting activities will be performed for the first floor respectively. In other words, reinforcement activity cannot be performed before completing the formworks activity, and concrete activity cannot be performed before completing reinforcement and so on.
According to the given data above, please draw the Activity on Node(A-o-A) diagram of this project.
Abbreviations: FW, RF, CON, PLA and PNT.

## Slide 37
Activity | Predecessor | Duration
A | - | 3
B | A (FS2) | 2
C | A (SS) | 2
D | B (SS1) | 4
E | C (SF3) | 1
F | C (FF3) | 2
G | D (SS1),E | 4
H | F (SF2),G | 3

## Slide 38
Act. | Days |  |  |  |  |  |  |  |  |  |  |  |  | 
A | X | X | X |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  | X | X |  |  |  |  |  |  | 
C | X | X |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  | X | X | X | X |  |  |  | 
E |  |  | X |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  | X | X |  |  |  |  |  |  |  |  | 
G |  |  |  |  |  |  |  | X | X | X | X |  |  | 
H |  |  |  |  |  |  |  |  |  |  |  | X | X | X
Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## Slide 39
0 |  | 0
Start |  | 
 | 0 | 
0 |  | 3
A |  | 
 | 3 | 
2 |  | 3
E |  | 
6 | 1 | 7
7 |  | 11
G |  | 
7 | 4 | 11
5 |  | 7
B |  | 
5 | 2 | 7
0 |  | 2
C |  | 
4 | 2 | 6
6 |  | 10
D |  | 
6 | 4 | 10
3 |  | 5
F |  | 
12 | 2 | 14
14 |  | 14
End |  | 
14 | 0 | 14
11 |  | 14
H |  | 
11 | 3 | 14
FS2
SS
SS1
SF3
FF3
SS1
SF2