## Slide 1: PROJECT MANAGEMENT AND PLANNING RESITATION

## Slide 2
Compress the given network fully. The direct cost is 10.000 TL.
TN = 36 days
C N = 10 000 TL
Critical path: B-C-D
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
Example 1.

## Slide 3: Forward Calculation
0
1
2
3
4
0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10

## Slide 4: Forward Calculation
0
1
2
3
4
0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10
30

## Slide 5: Forward Calculation
0
1
2
3
4
0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10
30
12

## Slide 6: Forward Calculation
0
1
2
3
4
0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10
30
12
36
36
22
If two arrows intersect each other at one event, you need to take the highest one as duration in the forward calculation.

## Slide 7: Backward Calculation
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10 10
30 30
12 22
36 36

## Slide 8: Backward Calculation
0
1
2
3
4
0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10
30 30
12 26
36 36

## Slide 9: Backward Calculation
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10 10
30 30
12 26
36 36
0
14
If two arrows intersect eachother at one event, you need to take the lowest one as duration in the backward calculation.

## Slide 10: Total Float Calculation
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10 10
30 30
12 26
36 36
ES
14
Definition: Total Float is the schedule ﬂexibility or amount of time that a schedule activity can be delayed or extended without delaying the project ﬁnish date.
LS
LF
EF
TF for B= LF-(ES+B - Activity Duration)
TF for B= 10-(0+10)=0

## Slide 11: Free Float Calculation
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10 10
30 30
12 26
36 36
ES
14
Definition: Free Float is the amount of time that a schedule activity can be delayed without delaying the early start date of any successor
LS
LF
EF
FF for B= EF-(ES+B - Activity Duration)
FF for B= 10-(0+10)=0
0/0
0/0
0/0
ES
EF
LF
TF for=30-(10+20)=0
FF for C=30-(10+20)=0
TF for A= 26 – (0+12)=14
FF for A=12-(0+12)=0
LS
EF
LF
TF for B= LF-(ES+B - Activity Duration)
TF for E=36-(12+10)=14
FF for E=36-(12+10)=14

## Slide 12: TF and FF Calculation
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10 10
30 30
12 26
36 36
ES
14
LS
LF
EF
0/0
0/0
0/0
TF for E Act.= 36 - (12+10)=14
FF for E Act.= 36 - (12+10)=14
TF for A Act.= 26 – (0+12)=14
FF for A Act.=12 – (0+12)=0
14/14
14/0

## Slide 13: Critical Path
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
20 10/200
10 10
30 30
12 26
36 36
ES
14
LS
LF
EF
0/0
0/0
0/0
14/14
14/0
Critical path: A series of interconnected activities through the network diagram, which cannot be delayed without increasing the duration of the project.  0/0

## Slide 14
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
10 0/200
New project duration = 26 days
New project cost = 10 000 + 10*200 = 12 000 TL
Critical path: B-C-D
* There is no network limitation since the compression of 10 days is smaller than the float of 14 days in the B-C-D path.
I. Crashing
Ex 1.
10 10
20 20
12 16
26 26
TF=10-(0+10)=0
FF=10-(0+10)=0
TF=20-(10+10)=0
FF=20-(10+10)=0
TF=0
FF=0
TF=4
FF=0
TF=4
FF=4

## Slide 15
0
1
2
3
4
0 0
B
E
D
C
A
10 6/300
6
10 1/400
12 9/100
10 0/200
New project duration = 26 days
New project cost = 10 000 + 10*200 = 12 000 TL
Critical path: B-C-D
* There is no network limitation since the compression of 10 days is smaller than the float of 14 days in the B-C-D path.
I. Crashing
Ex 1.
10 10
20 20
26 26
12 16
0/0
0/0
0/0
4/4
4/0

## Slide 16
0
1
2
3
4
0 0
B
E
D
C
A
6 2/300
6
10 1/400
12 9/100
10 0/200
T2 = 22 days
C2 = 12 000 + 4*300= 13 200 TL
Critical path: B-C-D and A-E
* There is a network limitation because if we compress B by 6 days, the parallel path which has a float of 4 days becomes automatically critical. That means, it would be waste of money if we compress B by more than 4 days.
II. Crashing
Ex 1.
9
0/0
0/0
0/0
0/0
0/0

## Slide 17
T3 = 20 days
C3= 13 200 + 100*2 + 300*2= 14 000 TL
For further compression, it must involve equal decreases in both critical paths, because otherwise the project duration will not be reduced. 1 st chain: B-C-D, 2 nd chain: A-E
There is a network limitation because if we compress A by 9 days, the 7 days will have no effect on the Final duration. B can only be compressed by 2 days
III. Crashing
0
1
2
3
4
0 0
B
E
D
C
A
4 0/300
6
10 1/400
10 7/100
10 0/200
1 st chain: B-C-D  B (300)
2 nd chain: A-E  A (100)
Ex 1.
4 4
14 14
20 20
10 10

## Slide 18
T4 = 20 days
C4= 14 000 + 7*100 + 400= 15 100 TL
That is why this compression is cometimes called as ‘’useless crash’’.
Once the activity on a critical chain have been fully crashed, then there is no possibility to compress the network further. There is no need to crash other activities since this will add to the cost but will have no effect on the project duration
To achieve ‘all crash’ situation:
IV. Crashing
0
1
2
3
4
0 0
B
E
D
C
A
4 0/300
6
9 0/400
3 0/100
10 0/200
1 st chain: B-C-D  B (300)
2 nd chain: A-E  A (100)
Ex 1.

## Slide 19
If the indirect cost is 230 ₺ / day, what is the optimum duration and associated cost? Draw the direct and indirect cost curves.
duration | direct | indirect |  | total
36 | 10000 | 230x36= | 8280 | 18280
35 | 10200 | 230x35= | 8050 | 18250
34 | 10400 | 230x34= | 7820 | 18220
33 | 10600 | 230x33= | 7590 | 18190
32 | 10800 | 230x32= | 7360 | 18160
31 | 11000 | 230x31= | 7130 | 18130
30 | 11200 | 230x30= | 6900 | 18100
29 | 11400 | 230x29= | 6670 | 18070
28 | 11600 | 230x28= | 6440 | 18040
27 | 11800 | 230x27= | 6210 | 18010
26 | 12000 | 230x26= | 5980 | 17980
25 | 12300 | 230x25= | 5750 | 18050
24 | 12600 | 230x24= | 5520 | 18120
23 | 12900 | 230x23= | 5290 | 18190
22 | 13200 | 230x22= | 5060 | 18260
21 | 13600 | 230x21= | 4830 | 18430
20 | 14000 | 230x20= | 4600 | 18600
20 | 15100 | 230x20= | 4600 | 19700
Chart: Days
| 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 20
 | 18280 | 18250 | 18220 | 18190 | 18160 | 18130 | 18100 | 18070 | 18040 | 18010 | 17980 | 18050 | 18120 | 18190 | 18260 | 18430 | 18600 | 19700
Chart: Days
| 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 20
 | 8280 | 8050 | 7820 | 7590 | 7360 | 7130 | 6900 | 6670 | 6440 | 6210 | 5980 | 5750 | 5520 | 5290 | 5060 | 4830 | 4600 | 4600
Chart: Days
| 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 28 | 27 | 26 | 25 | 24 | 23 | 22 | 21 | 20 | 20
 | 10000 | 10200 | 10400 | 10600 | 10800 | 11000 | 11200 | 11400 | 11600 | 11800 | 12000 | 12300 | 12600 | 12900 | 13200 | 13600 | 14000 | 15100
Topt = 26
Copt = 17980 ₺

## Slide 20
Example 2.
Find the least cost schedule for the network shown below.
Act | Duration |  | Cost | 
 | Normal | Crashed | Normal | Crashed
A | 4 | 2 | 400 ₺ | 500 ₺
B | 8 | 5 | 800 ₺ | 980 ₺
C | 3 | 2 | 600 ₺ | 700 ₺
D | 10 | 6 | 500 ₺ | 600 ₺
E | 8 | 6 | 800 ₺ | 950 ₺
F | 7 | 4 | 700 ₺ | 1.000 ₺
Overhead cost = 100 ₺ / day
(indirect cost)
0
B
E
D
C
A
3
7
10
8
4
8
F
1
2
3
4

## Slide 21
0
0 0
B
E
D
C
A
3
1/100
7
3/100
10
4/25
8
2/75
4
2/50
8
3/60
F
16 16
4 6
8 8
8 9
1
2
3
4

## Slide 22
Ex 2.
Act | Duration |  | Cost |  | 
 | Normal | Crashed | Normal | Crashed | slope
A | 4 | 2 | 400 ₺ | 500 ₺ | (500-400) / (4-2) = 50 ₺ / day
B | 8 | 5 | 800 ₺ | 980 ₺ | 60 ₺
C | 3 | 2 | 600 ₺ | 700 ₺ | 100 ₺
D | 10 | 6 | 500 ₺ | 600 ₺ | 25 ₺
E | 8 | 6 | 800 ₺ | 950 ₺ | 75 ₺
F | 7 | 4 | 700 ₺ | 1.000 ₺ | 100 ₺
Direct costs = 400 + 800 + 600 + 500 + 800+ 700 = 3800 ₺
Indirect costs = 16 x 100 = 1600 ₺
Total = 5400 ₺
0
0 0
B
E
D
C
A
3
1/100
7
3/100
10
4/25
8
2/75
4
2/50
8
3/60
F
16 16
4 6
8 8
8 9
1
2
3
4

## Slide 23
0
0 0
B
E
D
C
A
3
1/100
7
3/100
10
4/25
8
2/75
4
2/50
7
2/60
F
15 15
4 5
7 7
7 8
1
2
3
4
8-0=8
15-8=7

## Slide 24
Ex 2.
T1 = 15 days
D.C = 3800 + 60 = 3860 ₺
I.C = 15 x 100 = 1500 ₺
Total = 5360 ₺
I. Crash
0
0 0
B
E
D
C
A
3
1/100
7
3/100
10
4/25
8
2/75
4
2/50
7
2/60
F
15 15
4 5
7 7
7 8
1
2
3
4
Critical path = B60-E75
Crash B by 1

## Slide 25
Ex 2.
T2 = 14 days
D.C = 3860 + 60 = 3920 ₺
I.C = 14 x 100 = 1400 ₺
Total = 5320 ₺
II. Crash
0
0 0
B
E
D
C
A
3
1/100
7
3/100
10
4/25
8
2/75
4
2/50
6
1/60
F
14 14
4 4
6 6
6 7
1
2
3
4
Critical path = B60-E75
Crash B by 1

## Slide 26
Ex 2.
T2 = 14 days
D.C = 3860 + 60 = 3920 ₺
I.C = 14 x 100 = 1400 ₺
Total = 5320 ₺
II. Crash
0
0 0
B
E
D
C
A
3
1/100
7
3/100
10
4/25
8
2/75
4
2/50
6
1/60
F
14 14
4 4
6 6
6 7
1
2
3
4
Critical path = B60-E75
Crash B by 1

## Slide 27
Ex 2.
T3 = 13 days
D.C = 3920 + 60 + 25 = 4005 ₺
I.C = 13 x 100 = 1300 ₺
Total = 5305 ₺
III. Crash
0
0 0
B
E
D
C
A
3
1/100
7
3/100
9
3/25
8
2/75
4
2/50
5
0/60
F
13 13
4 4
5 5
5 6
1
2
3
4
Critical path = B60-E75 and A50-D25
Crash B and D by1

## Slide 28
Ex 2.
T3 = 13 days
D.C = 3920 + 60 + 25 = 4005 ₺
I.C = 13 x 100 = 1300 ₺
Total = 5305 ₺
III. Crash
0
0 0
B
E
D
C
A
3
1/100
7
3/100
9
3/25
8
2/75
4
2/50
5
0/60
F
13 13
4 4
5 5
5 6
1
2
3
4
Critical path = B60-E75 and A50-D25
Crash B and D by1

## Slide 29
Ex 2.
T4 = 12 days
D.C = 4005 + 75 + 25 = 4105 ₺
I.C = 12 x 100 = 1200 ₺
Total = 5305 ₺ (same with the third crash)
IV. Crash
0
0 0
B
E
D
C
A
3
1/100
7
3/100
8
2/25
7
1/75
4
2/50
5
0/60
F
12 12
4 4
5 5
5 5
1
2
3
4
Critical path = B60-E75 and A50-D25
Crash E and D by1

## Slide 30
Ex 2.
T5 = 11 days
D.C = 4105 + 75 + 25 + 100 = 4305 ₺
I.C = 11 x 100 = 1100 ₺
Total = 5405 ₺ (missed the optimum point)
*If one of the critical path is completely crashed (B-E), stop then.
V. Crash
0
0 0
B
E
D
C
A
3
1/100
6
2/100
7
1/25
6
0/75
4
2/50
5
0/60
F
11 11
4 4
5 5
5 5
1
2
3
4
Critical path = B60-E75 / A50-D25 / B60-F100
Crash E, D and F by 1

## Slide 31
Least cost = 5305 ₺
Optimum time 12 or 13 days
Chart: Days
| 16 | 15 | 14 | 13 | 12 | 11
 | 5400 | 5360 | 5320 | 5305 | 5305 | 5405

## Slide 32
Example 3.
Normal duration = 19 days
Normal cost = 25300 ₺
Indirect cost = 19 x 120 = 2280 ₺
Total cost = 27 580 ₺
1
B
E
D
C
A
6 (50,60,60)
F
4
3
2
7
6
5
14 14
6 6
5 6
4 6
0 0
G
I
H
14 15
19 19
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
4 (30,60,80)
4 (40,50)
10 (20,20,20)
5 (10,10,30,50)
d3
d2
d1
Normal Project cost=25300+120*19=27580

## Slide 33
Example 3.
Normal duration = 19 days
Normal cost = 25300 ₺
Indirect cost = 19 x 120 = 2280 ₺
Total cost = 27 580 ₺
1
B
E
D
C
A
6 (50,60,60)
F
4
3
2
7
6
5
14 14
6 6
5 6
4 6
0 0
G
I
H
14 15
19 19
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
4 (30,60,80)
4 (40,50)
10 (20,20,20)
5 (10,10,30,50)
d3
d2
d1
Normal Project cost=25300+120*19=27580

## Slide 34
Ex 3.
Normal duration = 18 days
Normal cost = 25300 + 10 = 25310 ₺
Indirect cost = 18 x 120 = 2160 ₺
Total cost = 27 470 ₺
1
B
E
D
C
A
6 (50,60,60)
F
4
3
2
7
6
5
14 14
6 6
5 6
4 6
0 0
G
I
H
14 14
18 18
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
4 (30,60,80)
4 (40,50)
10 (20,20,20)
4 (10,10,30,50)
d3
d2
d1
Critical path = A50-F80-H10
Crash H by 1
I. Crash
1st=A-F-H
2nd=A-F-3d-I
1Alt=A=50
2Alt=F=80
3Alt=H-I=10+30=40
Normal Project cost=25300+120*18+10=27470

## Slide 35
Ex 3.
Normal duration = 18 days
Normal cost = 25300 + 10 = 25310 ₺
Indirect cost = 18 x 120 = 2160 ₺
Total cost = 27 470 ₺
1
B
E
D
C
A
6 (50,60,60)
F
4
3
2
7
6
5
14 14
6 6
5 6
4 6
0 0
G
I
H
14 14
18 18
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
4 (30,60,80)
4 (40,50)
10 (20,20,20)
4 (10,10,30,50)
d3
d2
d1
Critical path = A50-F80-H10
Crash H by 1
I. Crash

## Slide 36
Ex 3.
T = 17 days
D.C= 25310 + 40 = 25350 ₺
I.C. = 17 x 120 = 2040 ₺
T.C = 27 390 ₺
1
B
E
D
C
A
6 (50,60,60)
F
4
3
2
7
6
5
14 14
6 6
5 6
4 6
0 0
G
I
H
14 14
17 17
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
3 (30,60,80)
4 (40,50)
10 (20,20,20)
3 (10,10,30,50)
d3
d2
d1
Critical path = A50-F80-H10 / A50-F80-I30
1) A  50,
2) F  80,
3) H + I  30+10=40
Decision H and I
II. Crash
1Alt.=A=50
2Alt.=F=80
3Alt.=H+I=30+60=90

## Slide 37
Ex 3.
T = 17 days
D.C= 25310 + 40 = 25350 ₺
I.C. = 17 x 120 = 2040 ₺
T.C = 27 390 ₺
1
B
E
D
C
A
6 (50,60,60)
F
4
3
2
7
6
5
14 14
6 6
5 6
4 6
0 0
G
I
H
14 14
17 17
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
3 (30,60,80)
4 (40,50)
10 (20,20,20)
3 (10,10,30,50)
d3
d2
d1
Critical path = A50-F80-H10 / A50-F80-I30
1) A  50,
2) F  80,
3) H + I  30+10=40
Decision H and I
II. Crash
2nd crashing cost=25300+120*17+10+10+30=27470

## Slide 38
Ex 3.
T = 16 days
D.C= 25350 + 50 = 25400 ₺
I.C. = 16 x 120 = 1920 ₺
T.C = 27 320 ₺
1
B
E
D
C
A
5 (50,60,60)
F
4
3
2
7
6
5
13 13
5 5
5 5
4 5
0 0
G
I
H
1313
16 16
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
3 (30,60,80)
4 (40,50)
10 (20,20,20)
3 (10,10,30,50)
d3
d2
d1
Critical path = A50-F80-H30 / A50-F80-I60
1) A  50,
2) F  80,
3) H + I  30+60=90
Decision A
III. Crash
0/0
0/0
0/0
0/0
2/2
0/0
0/0
0/0
2/2
1/1
1/0
2/2
1ALT=F=80
2Alt=B+A=100
3Alt=H+I=30+60=90

## Slide 39
Ex 3.
T = 16 days
D.C= 25350 + 50 = 25400 ₺
I.C. = 16 x 120 = 1920 ₺
T.C = 27 320 ₺
1
B
E
D
C
A
5 (50,60,60)
F
4
3
2
7
6
5
13 13
5 5
5 5
4 5
0 0
G
I
H
13 13
16 16
9 (30,30,30)
8 (80,110)
5 (40,50)
6 (30,30,40)
3 (30,60,80)
4 (40,50)
10 (20,20,20)
3 (10,10,30,50)
d3
d2
d1
Critical path = A50-F80-H30 / A50-F80-I60
1) A  50,
2) F  80,
3) H + I  30+60=90
Decision A
III. Crash

## Slide 40
Ex 3.
T = 15 days
D.C= 25400 + 80 = 25480 ₺
I.C. = 15 x 120 = 1800 ₺
T.C = 27 280 ₺
1
B
E
D
C
A
5 (50,60,60)
F
4
3
2
7
6
5
G
I
H
9 (30,30,30)
7 (80,110)
5 (40,50)
6 (30,30,40)
3 (30,60,80)
4 (40,50)
10 (20,20,20)
3 (10,10,30,50)
d3
d2
d1
Critical path = A60-F80-H30 / A60-F80-I60 / B40-F80-H30 / B40-F80-I60
1) A + B  60+40=100,
2) F  80,
3) H + I  30+60=90
Decision F
IV. Crash

## Slide 41
Ex 3.
T = 15 days
D.C= 25400 + 80 = 25480 ₺
I.C. = 15 x 120 = 1800 ₺
T.C = 27 280 ₺
1
B
E
D
C
A
5 (50,60,60)
F
4
3
2
7
6
5
12 12
5 5
5 5
4 5
0 0
G
I
H
12 12
15 15
9 (30,30,30)
7 (80,110)
5 (40,50)
6 (30,30,40)
3 (30,60,80)
4 (40,50)
10 (20,20,20)
3 (10,10,30,50)
d3
d2
d1
Critical path = A60-F80-H30 / A60-F80-I60 / B40-F80-H30 / B40-F80-I60
1) A + B  60+40=100,
2) F  80,
3) H + I  30+60=90
Decision F
IV. Crash

## Slide 42
Ex 3.
T = 14 days
D.C= 25480 + 90 = 25570 ₺
I.C. = 14 x 120 = 1680 ₺
T.C = 27 250 ₺
1
B
E
D
C
A
5 (50,60,60)
F
4
3
2
7
6
5
G
I
H
9 (30,30,30)
7 (80,110)
5 (40,50)
6 (30,30,40)
2 (30,60,80)
4 (40,50)
10 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
Critical path = A60-F110-H30 / A60-F110-I60 / B40-F110-H30 / B40-F110-I60
1) A + B  60+40=100,
2) F  110,
3) H + I  30+60=90
Decision H+I
V. Crash

## Slide 43
Ex 3.
T = 14 days
D.C= 25480 + 90 = 25570 ₺
I.C. = 14 x 120 = 1680 ₺
T.C = 27 250 ₺
1
B
E
D
C
A
5 (50,60,60)
F
4
3
2
7
6
5
12 12
5 5
5 5
4 4
0 0
G
I
H
12 12
14 14
9 (30,30,30)
7 (80,110)
5 (40,50)
6 (30,30,40)
2 (30,60,80)
4 (40,50)
10 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
Critical path = A60-F110-H30 / A60-F110-I60 / B40-F110-H30 / B40-F110-I60
1) A + B  60+40=100,
2) F  110,
3) H + I  30+60=90
Decision H+I
V. Crash

## Slide 44
Ex 3.
T = 13 days
D.C= 25570 + 120 = 25690 ₺
I.C. = 13 x 120 = 1560 ₺
T.C = 27 250 ₺
1
B
E
D
C
A
4 (50,60,60)
F
4
3
2
4
6
5
0 0
G
I
H
9 (30,30,30)
7 (80,110)
4 (40,50)
6 (30,30,40)
2 (30,60,80)
4 (40,50)
9 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
C. P. = A60-F110-H50 / A60-F110-I80 / A60-E30 / B40-F110-H50 / B40-F110-I80 / B40-E30 / C40-G20
1) A + B  60+40=100,
2) E + F  30+110=140,
3) H + I + E  50+80+30=160
Decision A + B + G
VI. Crash
Independent crash G by 1

## Slide 45
Ex 3.
T = 13 days
D.C= 25570 + 120 = 25690 ₺
I.C. = 13 x 120 = 1560 ₺
T.C = 27 250 ₺
1
B
E
D
C
A
4 (50,60,60)
F
4
3
2
4
6
5
11 11
4 4
4 4
4 4
0 0
G
I
H
11 11
13 13
9 (30,30,30)
7 (80,110)
4 (40,50)
6 (30,30,40)
2 (30,60,80)
4 (40,50)
9 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
C. P. = A60-F110-H50 / A60-F110-I80 / A60-E30 / B40-F110-H50 / B40-F110-I80 / B40-E30 / C40-G20
1) A + B  60+40=100,
2) E + F  30+110=140,
3) H + I + E  50+80+30=160
Decision A + B + G
VI. Crash
Independent crash G by 1

## Slide 46
Ex 3.
T = 12 days
D.C= 25690 + 150 = 25840 ₺
I.C. = 12 x 120 = 1440 ₺
T.C = 27 280 ₺
1
B
E
D
C
A
3 (50,60,60)
F
4
3
2
7
6
5
G
I
H
9 (30,30,30)
7 (80,110)
3 (40,50)
6 (30,30,40)
2 (30,60,80)
3 (40,50)
9 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
C.P.
A60-F110-H50
A60-F110-I80
A60-E30
B50-F110-H50
B50-F110-I80
B50-E30 C40-G20
C40-F110-H50
C40-F110-I80
C40-E30
VII. Crash
1) A + B + C  60+50+40=150,
2) E + F + G 30+110+20=160,
3) H + I + E + G  50+80+30+20=180
Decision A + B + C

## Slide 47
Ex 3.
T = 12 days
D.C= 25690 + 150 = 25840 ₺
I.C. = 12 x 120 = 1440 ₺
T.C = 27 280 ₺
1
B
E
D
C
A
3 (50,60,60)
F
4
3
2
7
6
5
10 10
3 3
3 3
3 3
0 0
G
I
H
10 10
12 12
9 (30,30,30)
7 (80,110)
3 (40,50)
6 (30,30,40)
2 (30,60,80)
3 (40,50)
9 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
C.P.
A60-F110-H50
A60-F110-I80
A60-E30
B50-F110-H50
B50-F110-I80
B50-E30 C40-G20
C40-F110-H50
C40-F110-I80
C40-E30
VII. Crash
1) A + B + C  60+50+40=150,
2) E + F + G 30+110+20=160,
3) H + I + E + G  50+80+30+20=180
Decision A + B + C

## Slide 48
Ex 3.
T = 11 days
D.C= 25840 + 160 = 26000 ₺
I.C. = 11 x 120 = 1320 ₺
T.C = 27320 ₺
1
B
E
D
C
A
3 (50,60,60)
F
4
3
2
7
6
5
9 9
3 3
3 3
3 3
0 0
G
I
H
9 9
11 11
8 (30,30,30)
6 (80,110)
3 (40,50)
6 (30,30,40)
2 (30,60,80)
3 (40,50)
8 (20,20,20)
2 (10,10,30,50)
d3
d2
d1
A- F110-H50
A- F110-I80
A- E30
B- F110-H50
B- F110-I80
B- E30 C50-G20
C50-F110-H50
C50-F110-I80
C50-E30
VIII. Crash
1) E + F + G 30+110+20=160,
2) H + I + E + G  50+80+30+20=180
Decision E + F + G = 160

## Slide 49
Ex 3.
T = 10 days
D.C= 26000 + 180 = 26180 ₺
I.C. = 10 x 120 = 1200 ₺
T.C = 27380 ₺
1
B
E
D
C
A
3 (50,60,60)
F
4
3
2
7
6
5
9 9
3 3
3 3
3 3
0 0
G
I
H
9 9
10 10
7 (30,30,30)
6 (80,110)
3 (40,50)
6 (30,30,40)
1 (30,60,80)
3 (40,50)
7 (20,20,20)
1 (10,10,30,50)
d3
d2
d1
IX. Crash
1) E + H + I + G 30+ 50 + 80 +20=180,
2) E + H + I + C  30+ 50 + 80 +50=210
Decision  E + H + I + G = 180
A –F -H50
A –F -I80
A -E30
B –F -H50
B –F -I80
B -E30 C50-G20
C50-F -H50
C50-F -I80
C50-E30

## Slide 50
Ex 3.
Topt = 13 -14
T.C for optimum duration= 27250 ₺
As at least one of the critical paths is completely crashed, we should stop then.
A –F -H50
A –F -I80
A -E30
B –F -H50
B –F -I80
B -E30 C50-G20
C50-F -H50
C50-F -I80

## Slide 51
Example 4.
C0 = 1000 ₺
C3 = 1175 ₺
C6 = 1420 ₺
T0= 20 days
1
7
B (3/30)
5
A (2/X1)
2
4
3
6
5
13
D (3/40)
6
C (3/50)
2
G (1/30)
10
E (2/X2)
12
F (3/20)
10
H (3/10)
Comb.

## Slide 52
Example 4.
C0 = 1000 ₺
C3 = 1175 ₺
C6 = 1420 ₺
T0= 20 days
1
7
B (3/30)
5
A (2/X1)
2
4
3
6
5
5 7
7 7
6 6
0 0
18 18
20 20
13
D (3/40)
6
C (3/50)
2
G (1/30)
10
E (2/X2)
12
F (3/20)
10
H (3/10)
B+C=80
B+F=50
B+G=60
D+C=90
D+F=60
D+G=70

## Slide 53
Ex 4.
C.P. = B30-D40 / C50-F20-G30
Crash B+F = 50
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
13
D (3/40)
6
C (3/50)
2
G (1/30)
10
E (2/X2)
11
F (2/20)
10
H (3/10)
I. Crash
T1 = 19 days
C1 = 1000 + 50 = 1050 ₺
Comb.

## Slide 54
Ex 4.
C.P. = B30-D40 / C50-F20-G30
Crash B+F = 50
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
5 6
6 6
6 6
0 0
17 17
19 19
13
D (3/40)
6
C (3/50)
2
G (1/30)
10
E (2/X2)
11
F (2/20)
10
H (3/10)
I. Crash
T1 = 19 days
C1 = 1000 + 50 = 1050 ₺
B+C=80
D+G=70
D+F=60

## Slide 55
Ex 4.
C.P. = B30-D40 / C50-F20-G30 / C50-D40
1) B+C  80
2) D+F  60
Decision  D+F
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
12
D (2/40)
6
C (3/50)
2
G (1/30)
10
E (2/X2)
10
F (1/20)
10
H (3/10)
II. Crash
T2 = 18 days
C2 = 1050 + 60 = 1110 ₺
Comb.
C3 = 1175 ₺  given by question

## Slide 56
Ex 4.
C.P. = B30-D40 / C50-F20-G30 / C50-D40
1) B+C  80
2) D+F  60
Decision  D+F
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
5 6
6 6
6 6
0 0
16 16
18 18
12
D (2/40)
6
C (3/50)
2
G (1/30)
10
E (2/X2)
10
F (1/20)
10
H (3/10)
II. Crash
T2 = 18 days
C2 = 1050 + 60 = 1110 ₺
B+C=80
D+G=70
D+E+F=60+X2
C3 = 1175 ₺  given by question

## Slide 57
Ex 4.
C.P.
B30-D40
B30-EX2-G30
C50-F20-G30
C50-EX2-G30
C50-D40
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
11
D (1/40)
6
C (3/50)
2
G (1/30)
9
E (1/X2=5)
9
F (0/20)
10
H (3/10)
III. Crash
T3 = 17 days
C3 = 1110 + 65 = 1175 ₺
1) B+C  80
2) D+F+E  60+X2
C3 =1175
1175-1110=65 must be total crash cost
Decision  D+F+E and X2=5
Comb.

## Slide 58
Ex 4.
C.P.
B30-D40
B30-EX2-G30
C50-F20-G30
C50-EX2-G30
C50-D40
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
5 6
6 6
6 6
0 0
15 15
17 17
11
D (1/40)
6
C (3/50)
2
G (1/30)
9
E (1/X2=5)
9
F (0/20)
10
H (3/10)
III. Crash
T3 = 17 days
C3 = 1110 + 65 = 1175 ₺
1) B+C  80
2) D+F+E  60+X2
C3 =1175
1175-1110=65 must be total crash cost
Decision  D+F+E and X2=5
B+C=80
D+G=70

## Slide 59
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
10
D (0/40)
6
C (3/50)
1
G (0/30)
9
E (1/5)
9
F (0/20)
10
H (3/10)
IV. Crash
T4 = 16 days
C4 = 1175 + 70 =1245 ₺
1) D+G  70
2) C+G  80
Decision  D+G
Comb.

## Slide 60
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
1
6
B (2/30)
5
A (2/X1)
2
4
3
6
5
5 6
6 6
6 6
0 0
15 15
16 16
10
D (0/40)
6
C (3/50)
1
G (0/30)
9
E (1/5)
9
F (0/20)
10
H (3/10)
IV. Crash
T4 = 16 days
C4 = 1175 + 70 =1245 ₺
1) D+G  70
2) C+G  80
Decision  D+G
B+C=80

## Slide 61
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
C50-H10
1
5
B (1/30)
5
A (2/X1)
2
4
3
6
5
10
D (0/40)
5
C (2/50)
1
G (0/30)
9
E (1/5)
9
F (0/20)
10
H (3/10)
V. Crash
T5 = 15 days
C5 = 1245 + 80 =1325 ₺
Crash  B+C = 80
Comb.

## Slide 62
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
C50-H10
1
5
B (1/30)
5
A (2/X1)
2
4
3
6
5
5 5
5 5
5 5
0 0
14 14
15 15
10
D (0/40)
5
C (2/50)
1
G (0/30)
9
E (1/5)
9
F (0/20)
10
H (3/10)
V. Crash
T5 = 15 days
C5 = 1245 + 80 =1325 ₺
Crash  B+C = 80
A+B+C=80+ X1
C6 = 1420 ₺

## Slide 63
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
C50-H10
1
4
B (0/30)
4
A (1/X1=15)
2
4
3
6
5
10
D (0/40)
4
C (1/50)
1
G (0/30)
9
E (1/5)
9
F (0/20)
10
H (3/10)
VI. Crash
T6 = 14 days
C6 = 1325+80+X1 = 1420 ₺
X1 = 15 ₺
Crash  A+B+C = 80 + X1
AX1-D40
AX1-E5-G30

## Slide 64
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
C50-H10
1
4
B (0/30)
4
A (1/X1=15)
2
4
3
6
5
4 4
4 4
4 4
0 0
13 13
14 14
10
D (0/40)
4
C (1/50)
1
G (0/30)
9
E (1/5)
9
F (0/20)
10
H (3/10)
VI. Crash
T6 = 14 days
C6 = 1325+80+X1 = 1420 ₺
X1 = 15 ₺
Crash  A+B+C = 80 + X1
AX1-D40
AX1-E5-G30

## Slide 65
Ex 4.
B30-D40
B30-E5-G30
C50-F20-G30
C50-E5-G30
C50-D40
C50-H10
Topt = 15, 16
Copt = 2525 ₺
AX1-D40
AX1-E5-G30
As one of the critical path (B-D) is completely crashed, we should stop then.
If the indirect cost is 80 ₺ / day, what is the optimum duration and associated cost?
Duration | Direct cost | Indirect cost | Total cost
20 | 1.000 ₺ | 80x20=1600 | 2.600 ₺
19 | 1.050 ₺ | 80x19=1520 | 2.570 ₺
18 | 1.110 ₺ | 1440 | 2.550 ₺
17 | 1.175 ₺ | 1360 | 2.535 ₺
16 | 1.245 ₺ | 1280 | 2.525 ₺
15 | 1.325 ₺ | 1200 | 2.525 ₺
14 | 1.420 ₺ | 1120 | 2.540 ₺
Chart: Days
| 20 | 19 | 18 | 17 | 16 | 15 | 14
 | 2600 | 2570 | 2550 | 2535 | 2525 | 2525 | 2540

## Slide 66
Example 5.
A company is to complete work packages of “formworks, reinforcement, concrete, plastering and painting Works” for a 3 storey residential building. Firstly, the work package for the first floor will be executed after that for second floor and finally the construction will be completed by executing the work packages for the third floor.
3rd Floor
2nd Floor
1st Floor
Assumptions: There are 5 activities which are formworks, reinforcement, concrete, plastering and painting. There is only one team for each of the activities. Firstly formworks activity will be performed for the first floor, after that reinforcement, concrete, plastering and painting activities will be performed for the first floor respectively. In other words, reinforcement activity cannot be performed before completing the formworks activity, and concrete activity cannot be performed before completing reinforcement and so on.
According to the given data above, please draw the Activity on Node(A-o-A) diagram of this project.
Abbreviations: FW, RF, CON, PLA and PNT.

## Slide 67
FW1

## Slide 68
Activity | Predecessor | Duration
A | - | 3
B | A (FS2) | 2
C | A (SS) | 2
D | B (SS1) | 4
E | C (SF3) | 1
F | C (FF3) | 2
G | D (SS1),E | 4
H | F (SF2),G | 3

## Slide 69
Act. | Days |  |  |  |  |  |  |  |  |  |  |  |  | 
A |  |  |  |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  |  |  |  |  |  |  |  |  | 
C |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  |  |  |  |  |  |  |  | 
E |  |  |  |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G |  |  |  |  |  |  |  |  |  |  |  |  |  | 
H |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## Slide 70
Act. | Days |  |  |  |  |  |  |  |  |  |  |  |  | 
A | X | X | X |  |  |  |  |  |  |  |  |  |  | 
B |  |  |  |  |  | X | X |  |  |  |  |  |  | 
C | X | X |  |  |  |  |  |  |  |  |  |  |  | 
D |  |  |  |  |  |  | X | X | X | X |  |  |  | 
E |  |  | X |  |  |  |  |  |  |  |  |  |  | 
F |  |  |  | X | X |  |  |  |  |  |  |  |  | 
G |  |  |  |  |  |  |  | X | X | X | X |  |  | 
H |  |  |  |  |  |  |  |  |  |  |  | X | X | X
Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## Slide 71
0 |  | 0
Start |  | 
 | 0 | 
0 |  | 3
A |  | 
 | 3 | 
2 |  | 3
E |  | 
6 | 1 | 7
7 |  | 11
G |  | 
7 | 4 | 11
5 |  | 7
B |  | 
5 | 2 | 7
0 |  | 2
C |  | 
4 | 2 | 6
6 |  | 10
D |  | 
6 | 4 | 10
3 |  | 5
F |  | 
12 | 2 | 14
14 |  | 14
End |  | 
14 | 0 | 14
11 |  | 14
H |  | 
11 | 3 | 14
FS2
SS
SS1
SF3
FF3
SS1
SF2